## Week 1
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 1
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
First client meeting and project overview | 1
Setting up our project page on Taiga.io | 2
City Selected: Vancouver | 1
Data Collection (minus DB polygons) | 8
Proposal and Statement of Work | 6
General Transit Feed System (GTFS) | 10
TOTAL | 28
ADDITIONAL COMMENTS

## Week 2
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 2
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Updated the CDB data wrangling file to output a CSV with standardized column names | 2
Discussed and planned out the high level data manipulation and score computing | 6
CDB and ODACF data filtering | 8
Develop time matrix using R5 | 8
Discussed method to develop score computations | 8
TOTAL | 32
ADDITIONAL COMMENTS

## Week 3
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 3
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Created visualization of scores in Vancouver using python | 6
Researched R Shiny and Dash for dahsboard visualizations | 6
TOTAL | 12
ADDITIONAL COMMENTS
Large number of interviews and interview preparation

## Week 4
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 4
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Created an outline for the final report | 2
Deployed Dashboard draft | 25
Team meeting and presentation | 3
TOTAL | 30
ADDITIONAL COMMENTS

## Week 5
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 5
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Researched methods to calculate transit efficiency scores | 8
Worked on publishing dashboard | 8
Converted dashboard to use HTMLs instead of Leaflet maps // Dashboard performance upgrade: added feature to call on pre-rendered HTML maps as opposed to performing computations on the fly | 8
Prepared presentation slides | 3
Added Kepler to dashboard | 1
TOTAL | 28
ADDITIONAL COMMENTS

## Week 6
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 6
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Developed effiency model and maps | 16
Wrote method-dashboard section of the report | 8
Recomputed travel time matrix, scores, and fresh HTML maps using the merged code with the most recent scoring function (check to see if all code is still functional) | 6
TOTAL | 30
ADDITIONAL COMMENTS

## Week 7
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 7
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Changed effiency model and maps | 8
Report writing/presentation | 20
TOTAL | 28
ADDITIONAL COMMENTS

## Week 8
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 8
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
Report writing/presentation/rehearsal | 20
Adhoc dashboard task | 8
TOTAL | 28
ADDITIONAL COMMENTS