## Week 1
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 1
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
First client meeting and project overview | 1
Setting up our project page on Taiga.io | 2
City Selection discussion Vancouver | 1
Obtaining Data for the project (Census dissemination blocks, Amenities, GTFS, OSM) | 8
Proposal and statement of work | 10
Software research | 6
Setting up Vancouver OSM and GTFS network on Open Trip Planner | 5
Team meetings | 3
TOTAL | 36
ADDITIONAL COMMENTS
Finding all the data was tricky as we were still trying to understand how to approach the problem and what we would need to do it.

## Week 2
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 2
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Discussed method to develop score computations | 8
Computed the travel time matrix using r5r | 6
More Software research and exploration. See Wiki links in Taiga.io | 6
Set up and filled the Github project log up until May 5 | 0.25
Discussed and planned out the high level data manipulation and score computing | 6
Wrote an initial DB score computation script and ran it using 3k of 15k origins at 36 departure times (generated a 36 billion row dataframe) | 10
Removed duplicate travel time matrix csvs | 0.25
Added wrangling feature for filtering by metropolitan area | 1
Weekly presentation slides | 1
TOTAL | 38.5
ADDITIONAL COMMENTS

## Week 3
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 3
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Wrote custom range normalization functions, scoring functions, improved score script comments, and created a accessibility score set folder | 18
Started ggplot visualizations in ggplot, tmap, and leaflet libraries | 3
Fixed small errors in score set exports and finished interactive map score visualization in leaflet | 2
Used scripting in gitbash (via jq library) to extract 36 megabytes of Vancouver polygon data from 1.6 gigabytes of Canada wide geoJson polygon data | 3
Team meetings | 4
Searched for cartographic shape file data | 4
Weekly presentation slides | 1
TOTAL | 35
ADDITIONAL COMMENTS

## Week 4
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 4
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Team meeting and presentation preparation | 3
Created HTML map renders for all score sets using a special score import function | 3
Explored downtown public library outlier point. Found that slight modifications of the coordinates fixes the problem which still has an unknown underlying cause | 4
Created an outline for the final report | 1
Added new convenience features to the score functions and other custom project functions | 5
Analyzed how and if it was important to address skewness in score distribution | 2
Started preparing slides for midterm presentation | 3
Weekly presentation slides | 1
Experimented with score distribution corrections and log corrections | 4
TOTAL | 26
ADDITIONAL COMMENTS
Experimenting with score distribution corrections involved developing functions in ggplot2 and incorporating new log normalization features to our existing custom functinos.

## Week 5
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 5
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Performed a full, very dirty and frustrating code merge: combined scripts for manipulating the travel time matrix (cleaning, scoring, etc.) and the scripts for visualization and output to have 1 main script for creating the HTML map renders. | 18
Cleaned repository of all unused data/files and moved to archive | 2
Developed functions to re-add NA values in the long score and isochrone frames. That way NA blocks can also be visualized | 6
Developed a dashboard performance upgrade to call on pre-rendered HTML maps as opposed to performing computations on the fly | 14
Researched methods to calculate transit efficiency scores | 4
Midterm presentation slides | 8
TOTAL | 52
ADDITIONAL COMMENTS
Was frustrating dealing with code merge. Team members weren't pushing merged code in the first place making everything very messy and hard to follow.
The dashboard was not meant to render and output prerendered html files making it extremely difficult to change the backend of the dashboard. Fixing this took a whole day and night and ended up using some nifty hack to help trick shiny into not re-rendering the html maps into the UI

## Week 6
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 6
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Recomputed travel time matrix, scores, and fresh HTML maps using the merged code with the most recent scoring function | 6
Full client deliverable code check to ensure everything was working properly | 4
Researched and wrote a thorough report introduction | 7
Experimented efficiency models via the difference in population quantiles / score quantiles | 3
Worked on the methods report section (data, computation, scoring) | 8
Team meetings | 4
Weekly presentation slides | 2
TOTAL | 34
ADDITIONAL COMMENTS

## Week 7
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 7
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Another long round of merging of all files with similar code | 12
Code review to complete the efficiency model and visualizations | 4
Directory reorganization for client delivery (and discarding of old archived content) | 4
Updated maps popup and created figures for report figures | 3
Analyzed the accessibility measure distributions | 3
Worked on report writing overall and subdivision analysis | 7
Re-rendering html maps for leaflet after each new update | 6
Worked on reorganizing some aesthetics of the dashboard about and data explorer page | 4
Fixed small bugs after recomputing the travel time matrix and scores | 5
Deployed preliminary dashboard on heroku | 1
Created ggplot2 violin plot visualizations | 2
Created the subdivision accessibility measure summary csv | 0.25
Preparation of the executive summary | 5
TOTAL | 56.25
ADDITIONAL COMMENTS

## Week 8
Luka Vukovic
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 8
Kelowna, BC
CLIENT
Statistics Canada - Joseph Kuchar, Bjenk Ellefsen
DESCRIPTION | HRs
Added draggable titles and page descriptions to the dashboard | 4
Worked on deploying the full dashboard and stack on heroku | 12
Deployed a cut down version of the dashboard via heroku | 7
Final presentation preparations | 15
Report writing, material criticism, and formatting. | 15
Edited other peoples parts to make writing more concise and clear, and added future work to the conclusion | 6
TOTAL | 59
ADDITIONAL COMMENTS
Heroku dashboard deploys have a 15min build limit, so if your stack cannot be built in 15 minutes it fails. We were using too many libraries which couldn’t be built in 15 minutes and this drastically affected dashboard deployment
We eventually cut out pages with deeper analysis since there simply wasn't an obvious way to get around this hurdle, despite it being possible to deploy the dashboard in a container via docker. Without enough experience with docker this was infeasible with our time constraints